## Schedule
Hot Topic 2015 GC & Vendor Delivery Schedule (New)
Project Information |  |  |  | Tasks and Delivery Schedule
Hot Topic # 2528 |  |  |  | Dates | Tasks |  | Vendor/Owner
|  |  |  | 2016-07-13 | GC & Vendor schedule is sent out to all vendors & IT |  | HT PM
Polo Park |  |  |  | 2016-07-25 | PM supplies Const. Admin Rep. with meter & vendor info |  | HT PM/Const. Admin Rep.
|  |  |  | 2016-08-22 | Pickup permit/pay fees |  | GC
Store's Mailing Address: |  |  |  | 2016-08-23 | Pre-con meeting with Ops Manager |  | GC
Hot Topic # 2528 |  |  |  | 2016-08-24 | Start Construction |  | GC
Polo Park |  |  |  |  | Barricade/snipe to arrive & Boston Barricade to install |  | The Garvey Group/Boston Barricade
1485 Portage Avenue |  |  |  | 2016-09-07 | Phone lines/DSL installed |  | Nancy B
Suite/Space # 240 |  |  |  |  | Order CC terminals from first data |  | Celeste Eager
Winnipeg, MN , Canada R3G 0W4 |  |  |  |  | Light package delivered |  | Midwest Lighting
District & Store Manager Contact Info: |  |  |  |  | Slatwall delivered |  | Spacewall
District Manager |  |  |  | 2016-09-14 | Brick delivered |  | Arto Brick
DM Number |  |  |  |  | Tech arrives to survey site (Low voltage), IT cabinet installed & rough cabling |  | Worldlink | Visit 1:
PM Contact Info: |  |  |  |  | Site survey and pre wiring for people counter |  | ShopperTrak | Survey phone lines and DSL present and active and test (phone call and surf with laptop)
Weston Martin |  |  |  |  | Sensormatic Rough-in |  | Sensormatic | Install Data Cabinet
310.938.5552 |  |  |  |  | Mobile shelving delivered (if applicable) |  | PIPP Mobile Shelving | Rough cable from data cabinet through conduits for cash wrap
wmartin@hottopic.com |  |  |  |  | Reeve equipment delivered |  | Reeve | Terminate cable in data cabinet
Construction Admin Rep Contact Info: |  |  |  |  | Project Manager mid trip |  | HT PM
Lisa Hernandez |  |  |  |  | New playnetwork player delivered to installer |  | Playnetwork
626.839.4681 x 1481 |  |  |  | 2016-09-15 | Mannequins arrive at HQ |  | Greneker
lisah@hottopic.com |  |  |  | 2016-09-21 | Sales floor fixtures delivered |  | Laurel
GC Contact Info: |  |  |  | 2016-09-27 | TV/Hardware delivered |  | Playnetwork
GC Name |  |  |  | 2016-10-03 | Construction box is delivered (Supplies for store) |  | DDS
GC Number |  |  |  |  | Spider track delivered |  | Rose Display
GC E-mail |  |  |  |  | Storefront sign installed |  | Anchor
Landlord Contact Info: |  |  |  |  | Sensormatic system installed |  | Sensormatic
Tenant Coordinator's Name |  |  |  |  | Tech arrives to install sound system |  | Playnetwork
Tenant Coordinator's Number |  |  |  | 2016-10-07 | Network equipment installed/tested & cable check up |  | Worldlink | Visit 2:
Tenant Coordinator's E-mail |  |  |  |  | Construction complete |  | GC | Install Router, Switch & DBU
Mall Operation's Name |  |  |  | 2016-10-08 | Construction clean |  | GC | Test with HD
Mall Operation's Number |  |  |  |  | ShopperTrak (people counter) installed |  | ShopperTrak | Terminate cables in cash wrap
Mall Operation's E-mail |  |  |  |  | POS equipment arrives |  | TNDC / Fujitsu
Previous Tenant: |  |  |  | 2016-10-10 | Tech arrives to support POS install & check out with Helpdesk |  | Worldlink/Fujitsu | Visit 3:
Previous Tenant's Name |  |  |  |  | Arcylic package delivered |  | Kaston | Support Fujitsu on POS install and finalize POS install and test with HD
*******NOTES TO VENDORS********* |  |  |  |  | Mannequin package delivered on Merch Truck |  | DC | Install laser printer
PlayNetwork; Sensormatic; Shoppertrak & Worldlink……….. |  |  |  | 2016-10-11 | Tech to arrive from Valuelink (Canada store only) |  | Celeste Eager | install phone
[5 empty] | Store supplies delivered |  | DDS
Low Voltage Permit is Required: |  |  |  |  | Walk thru with PM/Super (Punchlist) |  | HT PM/GC
(BL PM - refer to survey info provided to confirm) |  |  |  | 2016-10-13 | Turnover |  | HT PM/Store/DM
[5 empty] | Promo sign pack delivered |  | Archway
Union / Non-union (Y/N) - |  |  |  | 2016-10-19 | Final clean (Coordinate with DM) |  | GC/DM
How Many Storefront Openings (1 or2)? |  |  |  |  | Store opens for business |  | Store/DM
|  |  |  | 2016-11-18 | Close-out package is due |  | GC
Vendor Contact Info
Vendor | Name |  |  |  | Number | Fax | E-mail Address
Anchor Signs | Matthew Briggs |  |  |  | (843) 576-3294 | (843) 576-7273 | mbriggs@anchorsign.com
Archway |  |  |  |  | (770) 734-5108 |  | TeamHotTopic@archway.com
Arto Brick | George De Los Santos |  |  |  | (310) 768-8500 |  | george@artobrick.com
Boston Barricade | Tara Linn |  |  |  | 772-257-7328 | 772-257-7329 | tlinn@bostonbarricade.com
CIS Internet | Tom Bushman |  |  |  | 949-297-3579 |  | tom.bushman@cisvpn.com
Curley's Key Shop |  |  |  |  | (909) 622-6716 | (909) 469-1579 | Curleyskeyshop@verizon.net
DDS | Jacob Schulte |  |  |  | (612) 217-6308 |  | jschulte@ddsjit.com
Fujitsu | Michael Taglialavore |  |  |  | (425) 347-7012 | (408) 764-5014 | Michael.Taglialavore@us.fujitsu.com
Greneker | Steve Beckman |  |  |  | (323) 263-9000 x302 | (323) 980-1172 | Becks@greneker.com
Greneker | Susan Arica |  |  |  | 323-263-9000 x308 | 323-263-9543 | arics@greneker.com
Kaston | John Steger |  |  |  | (866) 943-5334 | (972) 243-5334 | john@kastongroup.com
Laurel | Anthony Ferrante |  |  |  | (856) 461-6600 | (856) 461-6622 | anthony@laurelmfg.com
Laurel | Dan Iosca |  |  |  | (856) 461-6600 | (856) 461-6622 | daniel.iosca@laurelmfg.com
Laurel | Blair Buchanan |  |  |  | (856) 461-6600 x306 | (856) 461-6622 | blair.b@laurelmfg.com
Midwest Lighting | Ano Gulasarian |  |  |  | (323) 957-6031 | (323) 462-2108 | ano@midwestlighting.com
PIPP Mobile | Brittany Mallay |  |  |  | 616-988-4082 | 616-791-9916 | bmallay@pippmobile.com
Playnetwork | Tony Boitano |  |  |  | (425) 629-2776 |  | hottopic_torrid@playnetwork.com
Radiant Global Logistics | Rosanna Rossi |  |  |  | (610) 586-5050 | (610) 586-5511 | rrossi.phl@radiantdelivers.com
Radiant Global Logistics | Carl Lewis |  |  |  | (610) 586-5050 | (610) 586-5511 | clewis.phl@radiantdelivers.com
Reeve | Clayton Frohwein |  |  |  | 951-202-5650 |  | claytonfrohwein@reeveco.com
Rose Display | Laurie Budrow |  |  |  | (800) 631-9707 x8103 |  | lbudrow@rosedisplays.com
Sensormatic | Cecilia Moreno |  |  |  | (310) 347-7351 | (818) 480-9465 | cemoreno@tyco.com
Sensormatic | Robert Benson |  |  |  | (714) 920-0905 |  | robenson@tycoint.com
ShopperTrak | Andrew Foley |  |  |  | (312) 529-5316 |  | afoley@shoppertrak.com
ShopperTrak | [6 empty] | orders@shoppertrak.com
Spacewall | Terry Sexton |  |  |  | (714) 961-1300 | (714) 961-0976 | tsexton@spacewallwest.com
The Garvey Group | Richard De La Rosa |  |  |  | (323) 551-6586 | (626) 484-1498 | richard.delarosa@thegarveygroup.com
Worldlink | Daren Harvey |  | (949) 861-2830 ext 221 |  | (917)-783-0729 |  | hottopicnewstores@worldlinkintegration.com

## HQ Distro
Name | Department | E-mail Address
Kristy Ribble | Store Ops | kribble@hottopic.com
Nanncy Bennett | Telecom | Nancyb@hottopic.com
Brian Higa | Network Services | Bhiga@hottopic.com
Lisa Hernandez | Construction | lisah@hottopic.com
Nicole Pavlinik | Construction | Npavlinik@hottopic.com
Dan Konoske | Construction | dkonoske@hottopic.com
Jason Hobbs | IT TNDC | Jhobbs@hottopic.com
Shane Turner | IT TNDC | Sturner@hottopic.com
Rana Chowdury | Helpdesk | rchowdury@hottopic.com
William Lee | Helpdesk | wlee@hottopic.com
Erik Lopez | Helpdesk | erikl@hottopic.com
Peggy Nishio | Purchasing | Pnishio@hottopic.com
Andrea Lewis | Marketing | alewis@hottopic.com
Dara Meas | Marketing | Dmeas@torrid.com
Jorge Carrillo | Tax | jcarrillo@hottopic.com
Kim Kinsey | Finance | kkinsey@hottopic.com
Emily Yoshihara | Purchasing | purchasing@hottopic.com
Cash Audit | Cash Audit | cashaudit@hottopic.com